## Test summary report
Tester | Đinh Mỹ Kỳ, Nguyễn Minh Uyên, Trương Nhật Minh, Phạm Việt Hoàng
Date | 2023-01-14
Function ID | Number of test cases | Number of passed test cases | Number of failed cases
UC20 | 6 | 6 | 0
UC01 | 2 | 1 | 1
UC02 | 3 | 2 | 0 | 1 (not tested yet)
UC07 | 3 | 1 | 0 | 2 (not automated testing yet)
UC08 | 1 | 1 | 0
UC09 | 6 | 6 | 0
UC10 | 2 | 2 | 0
UC11 | 2 | 2 | 0
UC12 | 2 | 2 | 0
UC13 | 3 | 2 | 1
UC14 | 1 | 1 | 0
UC15 | 3 | 2 | 1
UC16 | 1 | 0 | 1
UC17 | 2 | 1 | 1
UC18 | 2 | 0 | 2
UC19 | 1 | 1 | 0
UC20 | 2 | 1 | 0 | 1 (not tested yet)
UC22 | 4 | 4 | 0
Total | 46 | 35 | 7
Group:
TOTAL: | 46 test cases
PASS: | 75%
FAIL: | 15%
Not automated testing yet: | 10%
Đinh Mỹ Kỳ:
TOTAL: | 20 test cases
PASS: | 85%
FAIL: | 5%
Not automated testing yet: | 10%

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Cannot choose format for upload picture | User can upload any type of file (pdf, txt,...) instead of png and jpg only | UC01-UI01 | Low | Nguyễn Minh Uyên | 14/01/2023 | Open
B002 | Not yet design form for ebook upload |  | UC15-UI02 UC16-UI01 UC18-UI01 UC18-UI02 | Medium | Nguyễn Minh Uyên | 14/01/2023 | Open
B003 | Upload not enough pictures for ebook will not raise error |  | UC17-UI01 | Low | Nguyễn Minh Uyên | 14/01/2023 | Open
B004 | The book is in user's cart but not confirmed yet + User cannot go to borrow book to change day, time | From view cart does not link to borrow book page | UC13-UI03 | Low | Đinh Mỹ Kỳ | 14/01/2023 | Open
Note on D1: ====== ID#AAAAnDeyDuI Vu V. Nguyen (2023-01-12 03:00:54) Function ID of the function where the defect is found
Note on E1: ====== ID#AAAAnDeyDt8 Vu V. Nguyen (2023-01-12 03:00:54) High, Medium, or Low
Note on F1: ====== ID#AAAAnDeyDuE Vu V. Nguyen (2023-01-12 03:00:54) Name of the tester who reports the defect
Note on H1: ====== ID#AAAAnDeyDuA Vu V. Nguyen (2023-01-12 03:00:54) Open or Closed